## Sprint1
WEEK 1 (28thFeb - 6th March) - SPRINT 1
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Understand the requirements, explore other hotel websites & work on project sheet | Decide on scrum meetings & Setting up Project | None
Sharan Santosh Rachamalla | Figure out the components in the project | Setting up project tech stack | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Figure out the technologies | Setting up project tech stack & read about tech stack | None
Prerna Dattatray Garsole | Figure out the pages design to be included | Setting up project tech stack & read about tech stack | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We planned at meeting the requiremnts of the project in a simple and modular way. Emphasizing more on code resuability than to write repeated code number of times
2. Communication | We as a group dicussed which technology stack to adopt to meet the requirements. Everyone had pitched in different idea's on this but we deep dived into pros and cons of every tech stack and collectively came to a conclusion to use M.E.R.N

## Sprint2
WEEK 2 (7th March - 13th March) - SPRINT 2
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Sharan Santosh Rachamalla | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Configure the project i.e ReactJs & NodeJS | Create Architecture | None
Prerna Dattatray Garsole | Configure the project i.e MongoDB | Create Class Diagram | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We aimed at choosing simple yet efficient Databse i.e Mongo DB
2. Communication | Clearly communicated the tasks to be worked on and setting up the project stuctures for frontend and backend
3. Feedback | Feedback taken from team members and also implemented it for the folder structure setup in Backend