## Sprint1
Week #1 (4 days / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16*1) | D1 | D2 | D3 | D4
|  |  |  | 28/2/2022 | 2022-03-01 | 2022-03-02 | 2022-03-03
|  |  |  | 16 | 11 | 6 | 0 | Ideal Burndown
|  |  | 16 | 16 | 14 | 9 | 1 | Remaining Hrs (Total)
Requirement Analysis | Understand the requirements & explore other hotel sites | Akhil | 4 | 4 | 4 | 3 | 0
| Figure out the components | Sharan | 4 | 4 | 3 | 2 | 0
| Figure out the technologies | Raju | 4 | 4 | 4 | 0 | 1
| Figure out the pages design to be included | Prerna | 4 | 4 | 3 | 4 | 0
Team:
Akhil | 4 hours / Week
Sharan | 4 hours / Week
Raju | 4 hours / Week
Prerna | 4 hours / Week
Total Available Hours During Sprint 1: | 16

## Sprint2
Week #2 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 24*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-07-03 | 2022-08-03 | 2022-09-03 | 2022-10-03
|  |  |  | 24 | 15 | 7 | 0
|  |  | 24 | 24 | 12 | 10 | 3
Environment Setup | Configure the project tech stack i.e ReactJS & Node | Akhil | 6 | 6 | 3 | 3 | 0
| Configure the project tech stack i.e ReactJS & Node | Sharan | 6 | 6 | 2 | 2 | 3
| Configure the project tech stack i.e ReactJS | Raju | 6 | 6 | 4 | 3 | 0
| Configure the project tech stack i.e MongoDB | Prerna | 6 | 6 | 3 | 2 | 0
Team:
Akhil | 6 hours / Week
Sharan | 6 hours / Week
Raju | 6 hours / Week
Prerna | 6 hours / Week
Total Available Hours During Sprint 2: | 24