## Sprint1
Week #1 (4 days / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16*1) | D1 | D2 | D3 | D4
|  |  |  | 28/2/2022 | 2022-03-01 | 2022-03-02 | 2022-03-03
|  |  |  | 16 | 11 | 6 | 0 | Ideal Burndown
|  |  | 16 | 16 | 14 | 9 | 1 | Remaining Hrs (Total)
Requirement Analysis | Understand the requirements & explore other hotel sites | Akhil | 4 | 4 | 4 | 3 | 0
| Figure out the components | Sharan | 4 | 4 | 3 | 2 | 0
| Figure out the technologies | Raju | 4 | 4 | 4 | 0 | 1
| Figure out the pages design to be included | Prerna | 4 | 4 | 3 | 4 | 0
Team:
Akhil | 4 hours / Week
Sharan | 4 hours / Week
Raju | 4 hours / Week
Prerna | 4 hours / Week
Total Available Hours During Sprint 1: | 16

## Sprint2
Week #2 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 24*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-07-03 | 2022-08-03 | 2022-09-03 | 2022-10-03
|  |  |  | 24 | 15 | 7 | 0
|  |  | 24 | 24 | 12 | 10 | 3
Environment Setup | Configure the project tech stack i.e ReactJS & Node | Akhil | 6 | 6 | 3 | 3 | 0
| Configure the project tech stack i.e ReactJS & Node | Sharan | 6 | 6 | 2 | 2 | 3
| Configure the project tech stack i.e ReactJS | Raju | 6 | 6 | 4 | 3 | 0
| Configure the project tech stack i.e MongoDB | Prerna | 6 | 6 | 3 | 2 | 0
Team:
Akhil | 6 hours / Week
Sharan | 6 hours / Week
Raju | 6 hours / Week
Prerna | 6 hours / Week
Total Available Hours During Sprint 2: | 24

## Sprint3
Week #3 (4 days / week3)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17
|  |  |  | 32 | 21 | 10 | 0 | Ideal Burndown
|  |  | 32 | 29 | 19 | 9 | 0 | Remaining Hrs (Total)
Design | Database Design | Akhil | 8 | 8 | 6 | 3 | 0
| Database Design | Sharan | 8 | 8 | 5 | 2 | 0
| Architecture Diagram | Raju | 8 | 8 | 4 | 3 | 0
| Class Diagram | Prerna | 8 | 5 | 4 | 1 | 0
Team: | 8 hours / Week
Akhil | 8 hours / Week
Sharan | 8 hours / Week
Raju | 8 hours / Week
Prerna
Total Available Hours During Sprint 3: | 32

## Sprint4
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 25 | 18 | 9 | 0
Initial components setup, creating wireframes and basic logic implementation | Search API | Akhil | 8 | 8 | 6 | 2 | 0
| Holiday & Weekend Pricing | Sharan | 8 | 5 | 3 | 2 | 0
| Sign Up & Login API | Raju | 4 | 4 | 4 | 2 | 0
| Design wireframes for Sign Up & Login | Prerna | 8 | 8 | 5 | 3 | 0
Team:
Akhil | 8 hours / Week
Sharan | 8 hours / Week
Raju | 8 hours / Week
Prerna | 8 hours / Week
Total Available Hours During Sprint 4: | 32

## Sprint5
Week #5 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 28 | 24 | 10 | 0
Desgning logic for Login, Signup, Admin & Hotel Components | Search UI & Admin API | Akhil | 8 | 8 | 5 | 2 | 0
| Hotel Page(UI) | Sharan | 8 | 8 | 10 | 4 | 0
| Logout & User Profile Backend | Raju | 8 | 8 | 6 | 3 | 0
| Wireframes HotelPage, Login & Sign up | Prerna | 4 | 4 | 3 | 1 | 0
Team:
Akhil | 8 hours / Week
Sharan | 8 hours / Week
Raju | 8 hours / Week
Prerna | 8 hours / Week
32
Total Available Hours During Sprint 5:

## Sprint6
Week #6 (4 days / week)
| Task | Task Owner | Initial Estimate (Total Sprint Hours = 32*1) | D1 | D2 | D3 | D4
|  |  |  | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07
|  |  |  | 32 | 22 | 12 | 0
|  |  | 32 | 32 | 21 | 8 | 0
UI for Admin, Room & User Profile | Admin UI | Akhil | 8 | 8 | 5 | 2 | 0
| Room UI | Sharan | 8 | 8 | 7 | 3 | 0
| User Profile UI | Raju | 8 | 8 | 4 | 1 | 0
| User Profile Wireframe | Prerna | 8 | 8 | 5 | 2 | 0
Team:
Akhil | 8 hours / Week
Sharan | 8 hours / Week
Raju | 8 hours / Week
Prerna | 8 hours / Week
Total Available Hours During Sprint 5: | 32