## Sprint1
WEEK 1 (28thFeb - 6th March) - SPRINT 1
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Understand the requirements, explore other hotel websites & work on project sheet | Decide on scrum meetings & Setting up Project | None
Sharan Santosh Rachamalla | Figure out the components in the project | Setting up project tech stack | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Figure out the technologies | Setting up project tech stack & read about tech stack | None
Prerna Dattatray Garsole | Figure out the pages design to be included | Setting up project tech stack & read about tech stack | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We planned at meeting the requiremnts of the project in a simple and modular way. Emphasizing more on code resuability than to write repeated code number of times
2. Communication | We as a group dicussed which technology stack to adopt to meet the requirements. Everyone had pitched in different idea's on this but we deep dived into pros and cons of every tech stack and collectively came to a conclusion to use M.E.R.N

## Sprint2
WEEK 2 (7th March - 13th March) - SPRINT 2
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Sharan Santosh Rachamalla | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Configure the project i.e ReactJs & NodeJS | Create Architecture | None
Prerna Dattatray Garsole | Configure the project i.e MongoDB | Create Class Diagram | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We aimed at choosing simple yet efficient Databse i.e Mongo DB
2. Communication | Clearly communicated the tasks to be worked on and setting up the project stuctures for frontend and backend
3. Feedback | Feedback taken from team members and also implemented it for the folder structure setup in Backend

## Sprint3
WEEK 3 (14th March - 20th March) - SPRINT 3
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed database schema for hotels & bookings | Create Search API | None
Sharan Santosh Rachamalla | Completed database schema for users & rooms | Figure out holiday, weekend & seasonal pricing logic | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed architecture diagram | Create Signup & login API | None
Prerna Dattatray Garsole | Completed class diagram | Design wireframes for SignUp & Login | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We came up with simple schema's for DB avoid large data in one single document
2. Communication | We communicated and decided on which modules everybody has to work
3. Feedback | According to the feedback from everyone, we decided to go with two two different schemas for hotel and room rather tha putting rooms inside hotel schema itself

## Sprint4
WEEK 4 (21st March - 27th March) - SPRINT 4
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Search API | Create Search UI & Work on Admin API | None
Sharan Santosh Rachamalla | Completed logic for holiday, weekend & seasonal pricing | Create Hotel UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed sign up & login apis | Create logout & userprofile API | None
Prerna Dattatray Garsole | Completed wireframes design for signup & login | Create wireframes for Hotel Page & UI pages for Login & Sign Up | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We came up with simple wire frame designs
2. Communication | Everybody participated in communicating their respective API contracts and deciding on API handling

## Sprint5
WEEK 5 (28th March - 4th April) - SPRINT 5
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Search UI & Admin CRUD APIs | Create Admin UI | None
Sharan Santosh Rachamalla | Completed Hotel UI | Create Room UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed logout & userprofile APIs | Create User Profile UI | None
Prerna Dattatray Garsole | Completed Hotel Wireframe & UI Pages for Singup & Login | Create User Profile Wireframe | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on a simple User Interface Design for our website using Bootstrap
2. Communication | Everybody communicated on how their respective frontend components will be interacting with other's backend their contact and request response
3. Feedback | Everybody provided feedback on using redux in frontend for state management and not context API because of its redux simplicity

## Sprint6
WEEK 6 (4th April - 10th April) - SPRINT 6
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Admin UI | Create CRUD Bookings API | None
Sharan Santosh Rachamalla | Completed Room UI | Create Bookings UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed User Profile UI | Create Mockdata for tables & Start Testing | None
Prerna Dattatray Garsole | Completed User Profile Wireframe | Create Bookings Wireframe | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on a simple Room Booking UI
2. Communication | Everybody communicated their ideas on how to meet the Admin related requirements
3. Feedback | All the feedback regarding the wireframes was taken positively and implemented accordingly to the UI

## Sprint7
WEEK 7 (11th April - 17th April) - SPRINT 7
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed CRUD Bookings API | Start fixing the bugs | None
Sharan Santosh Rachamalla | Completed Bookings UI | Start fixing the bugs | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Created Mockdata & did Testing | Get Info about AWS Deployment | None
Prerna Dattatray Garsole | Completed Bookings Wireframe | Testing Parallely While others fixing bugs | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | Decided to use simple react hooks for Frontend rendering
2. Respect | Everybody respected other's decision to follow their own coding styles and practices
3. Courage | Everybody had courage to communicate few bugs or design flaws in their components and took help from other team members to resolve these