## Sprint1
WEEK 1 (28thFeb - 6th March) - SPRINT 1
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Understand the requirements, explore other hotel websites & work on project sheet | Decide on scrum meetings & Setting up Project | None
Sharan Santosh Rachamalla | Figure out the components in the project | Setting up project tech stack | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Figure out the technologies | Setting up project tech stack & read about tech stack | None
Prerna Dattatray Garsole | Figure out the pages design to be included | Setting up project tech stack & read about tech stack | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We planned at meeting the requiremnts of the project in a simple and modular way. Emphasizing more on code resuability than to write repeated code number of times
2. Communication | We as a group dicussed which technology stack to adopt to meet the requirements. Everyone had pitched in different idea's on this but we deep dived into pros and cons of every tech stack and collectively came to a conclusion to use M.E.R.N